## Sheet1
Days Left | Ideal Work | Actual Work |  | Work Notes
15 | 11 | 11 |  | Creation Of A Data Dictionary
14 | 11 | 11 |  | Create a Data Dictionary Which Outline the information on the tables and fields in the database
13 | 10 | 11 |  | Defining the Database Structure
12 | 10 | 10 |  | design the structure of the database
11 | 9 | 10 |  | Normalization of data
10 | 8 | 10 |  | normalise the fields in the database
9 | 8 | 9 |  | Creation of an Entity Relationship Diagram (ERD)
8 | 7 | 9 |  | Defining Security Features of the Website
7 | 6 | 9 |  | Defining User Access Control for the website
6 | 6 | 8 |  | define user access levels for the various users of the website and to distinguish features for each user level
5 | 5 | 8 |  | Defining appropriate validation checks for the website
4 | 4 | 7 |  | appropriately define validation checks for the different pages on the website in accordance with the security features
3 | 3 | 6 |  | Creation of a Mental Map/Navigation Map
2 | 2 | 5 |  | create a Navigation Map of the website displaying the website navigation
1 | 1 | 5 |  | Creation of a draft website design (Wireframe)
0 | 0 | 4 |  | finished
go