## Sheet1
Ideal Work | Days left | Actual Work | Work Notes
11 | 15 | 11 | Defining the Project Overview and Initiation
10 | 14 | 11 | Defining the Target Audience
9 | 13 | 11 | Estimation of project duration and creation of the Progress Chart
9 | 12 | 10 | Estimation of project duration and creation of the Progress Chart
8 | 11 | 10 | Defining of a Sprint Breakdown for the Project
8 | 10 | 9 | Defining of a Sprint Breakdown for the Project
8 | 9 | 8 | Defining of a Sprint Breakdown for the Project
7 | 8 | 7 | The designing of a Logo and Banner Design
6 | 7 | 6 | Deciding on the Programming Language to use
5 | 6 | 6 | Deciding on the Database Technology to use
4 | 5 | 6 | Deciding on Assumptions
4 | 4 | 5 | Deciding on Assumptions
3 | 3 | 5 | Defining of General Requirements
2 | 2 | 4 | Defining of Functional Requirements
1 | 1 | 4 | Defining of Non-Functional Requirements
0 | 0 | 3 | Finished